## Siilo Bug Report
SIILO BUG REPORT
BUG ID |  |  |  | BUG OVERVIEW |  | ENVIRONMENT |  | BUG DETAILS |  |  | BUG TRACKING |  |  |  | FIX |  | NOTES
BUG ID | TITLE | REPORTED BY | DATE REPORTED | SUMMARY | SCREENSHOT | DEVICE | OPERATING SYSTEM | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | DEFECT SEVERITY | DEFECT PRIORITY | ASSIGNED TO | STATUS | RESOLUTION | DATE OF FIX | NOTES | SEVERITY | DEFECT PRIORITY | STATUS
BugID_01 | MaxtheFaxScreen_Appcrash_I changed my mind option | Dhanashree | 2020-07-17 | The Siilo app crashes when I changed my mind option is selected on Max the fax screen | Video File name -ChangedmyMind_AppCrash | Android mobile phone | Android OS | 1. Open Siilo App on the mobile device 2. Click on I'm new to Siilo on welcome screen 3. Click on - No, I prefer to continue sending good ol' faxes button on terms screen 4. Click on "I changed my mind!" on Max the fax screen | User should be navigated to terms screen | App crashed | Major | High |  | Open |  |  |  | Showstopper | Critical | Open
BugID_02 | Intermittent Issue_Appcrash_Select back button from Max the fax_Reach welcome screen | Dhanashree | 2020-07-17 | The Siilo app crashes when user selects back button from Max the fax screen to reach welcome screen | Not 100% times reproducible | Android mobile phone | Android OS | 1. Open Siilo App on the mobile device 2. Click on I'm new to Siilo on welcome screen 3. Click on - No, I prefer to continue sending good ol' faxes button on terms screen 4. Select back button on Max the fax screen 5. Select back button on terms screen 6. Reach to the Welcome screen | User should be allowed to make new choice on welcome screen | App crashed | Major | High |  | Open |  |  |  | Major | High | Resolved
BugID_03 | Intermittent Issue_Sillo app crashes on welcome screen (Note - This issue was faced intermittent ) | Dhanashree | 2020-07-17 | Sillo app crashes intermittently on welcome screen | Not 100% times reproducible | Android mobile phone | Android OS | 1. Open Siilo App on the mobile device 2. User reaches Welcome screen | User should be allowed to make choice on welcome screen | Intermittent issue of app crashing and user exits | Major | Medium |  | Open |  |  |  | Minor | Medium | Closed
BugID_04 | Extra junk text present on terms and conditions button | Dhanashree | 2020-07-17 | Extra characters <b><u> <u></b> is seen between read word on terms and condition button | File name - ExtraCharacters_Terms and conditions | Android mobile phone | Android OS | 1. Open Siilo App on the mobile device 2. Click on I'm new to Siilo on welcome screen 3. Validate text on terms and condition button | "Please read and agree with our terms and conditions" message should be present | <b><u> <u></b> is seen on the message | Low | Low |  | Open |  |  |  | Low | Low
BugID_05 | Professions screen_Keyboard appears | Dhanashree | 2020-07-17 | Keyboard appears on Profession screens | File name -Keyboard_appears | Android mobile phone | Android OS | 1. Open Siilo App on the mobile device 2. Click on I'm new to Siilo on welcome screen 3. Click Yes, I agree button on terms screen 4. Enter first and last name on Names screen 5. Click on Next button | Keyboard prompt should not be visible on Professions screen | Keyboard prompt appears on Professions screen | Minor | Medium |  | Open
BugID_06 | Names screen_Next button enabled_Only Last name entered (Assumption - Next button enables when fisrt and last name entered) | Dhanashree | 2020-07-17 | Next button on Names screen enables when only last name is mentioned , if only first name is entered button is still inactive | Video file name -NamesScreen_NextButton | Android mobile phone | Android OS | 1. Open Siilo App on the mobile device 2. Click on I'm new to Siilo on welcome screen 3. Click Yes, I agree button on terms screen 4. Enter last name on Names screen 5. Validate Next button 6. Enter first name 7. Validate Next button | Next button should be active when firsnt and last name are entered (Assumption) | When only First name entered - Next button Inactive When only Last name entered - Next button active | Major | Medium |  | Open
BugID_07 | Profession screen_App crash_Multiple options selected | Dhanashree | 2020-07-17 | App is crashing when multiple options are selected on Professions screen at the same time | Video file name -ProfessionsScreen_MultipleChoices | Android mobile phone | Android OS | 1. Open Siilo App on the mobile device 2. Click on I'm new to Siilo on welcome screen 3. Click Yes, I agree button on terms screen 4. Enter first and last name on Names screen 5. Click on Next button 6. Select 2 professions at the same time on Professions screen | User should be allowed to select only 1 profession at a time | App crashed | Major | High |  | Open
BugID_08 | Profession screen_Profession Button color_Not changed to dark blue | Dhanashree | 2020-07-17 | As per user story 5 , on selection of profession button color changes to dark blue and "Next" appears on the right. The text "Best job ever! ". Currently , button color is not tunring dark blue and next and message doesn’t appear | Funcationality not present in current app | Android mobile phone | Android OS | 1. Open Siilo App on the mobile device 2. Click on I'm new to Siilo on welcome screen 3. Click Yes, I agree button on terms screen 4. Enter first and last name on Names screen 5. Click on Next button 6. Select 1 profession | As per user story 5 , on selection of profession button color changes to dark blue and "Next" appears on the right. The text "Best job ever! ". | Currently , button color is not tunring dark blue and next and message doesn’t appear | Minor | Low |  | Open
BugID_09 | Profession screen_First name_Not displayed | Dhanashree | 2020-07-17 | First name is not displayed on profession screen as per entered on Names screen | File name - Firstname_NotDisplayed_ProfessionsScreen | Android mobile phone | Android OS | 1. Open Siilo App on the mobile device 2. Click on I'm new to Siilo on welcome screen 3. Click Yes, I agree button on terms screen 4. Enter first and last name on Names screen 5. Click on Next button 6. Validate Firsnt name entered on Profession screen | Thanks [first name], now choose your profession. | Thanks %s, now choose your profession. Above text %s is displayed instaed of first name | Minor | Medium |  | Open
BugID_10 | Junk characters accepted_Phone number screen | Dhanashree | 2020-07-17 | Junk charatcers like !@&^#%#^ are accepted in Phone number field | File name -JunkCharacters_PhoneNumber | Android mobile phone | Android OS | 1. Open Siilo App on the mobile device 2. Click on I'm new to Siilo on welcome screen 3. Click Yes, I agree button on terms screen 4. Enter first and last name on Names screen 5. Click on Next button 6. Select any 1 profession 7. Enter email ID and click next 8. Verify email ID and click next 9. Select required country code 10. Enter junk data for phone number and click on next button | Junk data should not be allowed to enter and proceed | Junk charatcers like !@&^#%#^ are accepted in Phone number field | Major | Medium |  | Open
BugID_11 | Selection mode ON_appears on next screen | Dhanashree | 2020-07-17 | Selection mode is ON and appears on Next screens | File name - Selection mode_ON | Android mobile phone | Android OS | 1. Open Siilo App on the mobile device 2. Click on I'm new to Siilo on welcome screen 3. Click Yes, I agree button on terms screen 4. Enter first and last name on Names screen 5. Select All first name 6. Click on Next button 7. Observe the Professions screen | Selection mode should not be ON on next screens | Selection mode is ON on next all screeens | Minor | Low |  | Open